| Week | Focus | Deliverables |
| --- | --- | --- |
| 1 | - PhysMoP visualization (predictions + input data) - Document conducted tests so far | - Visual output of PhysMoP predictions - Draft “Methodology” & “Setup” sections |
| 2 | - Run experiments: GCNext vs PhysMoP across actions, body parts, time anchors - Real-time evaluation: latency, prediction time, stability - Start noting early model limitations | - Plots: MPJPE vs frames/actions - Raw notes on weak points - Simulated Real-time benchmarks - Visual comparisons (e.g. frame-by-frame GIFs) |
| 3 | - Create synthetic data for “stress” tests - Generalization test with dancing or new motion type data - Continue noting limitations | - Extended results section - Hypothesis testing notes |
| 4 | - Finish all experiments - Analyze specific failure cases - Focus: what real-time constraints are limiting the model | - Hypothesis testing notes - Real-time bottlenecks |
| 5 & 6 | - Focus: model limitations + how to improve them - Try first fixes (e.g. different pre-processing, tweaks to model structure) - Compare to baseline models | - Hopefully a working improved model |
| 7 | - Finalize the improved models - Note down the performance changes? |  |

Investigate the limitations of current human motion prediction models in real-time applications. By finding these limitations the aim will be to recommend (and maybe even test) possible improvements to current models for real-time applications.